## Test Plan
Test Plan
Core items | Sub-items
Test Enviroment | User Group | All normal people who understands Bengali & English
| Operation System | Windows, Mac, Linux
| Device | PC, Laptop, Android-run phone, iOS-run phone
| Browsers(including web version in mobile) | Firefox,Chrome,Edge,Opera mini, Safari
Subjects under Test/Scope | Features | User sign up
User login
User logout
Product browsing functionaity for all users
Product searching functionaity for all users
Searching functionality using different search parameters
Displaying product info in Product detail page
Language support
Product carting/wishlisting functionality for logged-in users
Product purchasing functionality for logged-in users
Account update functionality for logged-in users
Registering/login using social accounts, e.g. google/facebook etc
Notification functionality on product purchase
Payment option using card for logged-in users
Testing methods to be followed | Manual Testing(Black box) | Functional testing of different features
UI/UX related testing
Performance testing of different web-elements from UI
Backend API testing
Security testing covering security-related test cases
Monkey Testing on UI components
Accessibility testing for both English & Bengali
Compatibility testing in different OS,device & browsers
Exploratory load testing of APIs & different UI paths
Testing access-control of URLs & pages for public/authenticated users
| Manual Testing(White box) | Code review of different code blocks implementing different utilities based on different conditions
| Automation Testing | End-to-end browser-based automation testing using selenium for PC devices
End-to-end browser-based automation testing using appium for web-version in mobile devices
End-to-end automation testing using appium for mobile apps
Automated API testing
Automated Load testing
Automated unit tests of different classes/utilities from backend & different UI components [to be done by developers]
| Additional | Smoke testing for each new build
Sanity testing after each bug fix
Regression testing for each new build
Installation testing for each new build in different devices/OS
Testing tools/libraries | End-to-end automation(PC) | Selenium with Python test libraries(pytest,unittest)
| End-to-end automation(mobile) | Appium with Python test libraries(pytest,unittest)
| API automation | Postman initially. Then move to Python test libraries(pytest,unittest) for more custom test cases.
| Load testing automation | JMeter
| Unit tests | As per developer prefers
Testing Approach | Agile iterative approach
Exit criteria | At least 99% of all testcases should be passed including all security tests
QA deliverables | Detailed Test plan document, Testcase documentation, Bug report for each sprint, test report for each sprint

## Testcases
Testcases Document
ID | Test Case
1 | Test if public users can access the site from different OS/device/browsers
2 | Test if public user can browse different products
3 | Test if public user can search for different products
4 | Test if user can switch language from BN to EN and vice-versa
5 | Test if user can register using google mail & facebook
6 | Test if user can register using form data in sign up page
7 | Test with different valid & invalid values for form data in sign up page
8 | Test if user can login without registering into system
9 | Test if user can login after registering with google mail & facebook
10 | Test if user can login after registering with form data from signup page
11 | Test with different valid & invalid values for form data in login up page
12 | Test sign up with same mobile/email from existing user
13 | Test with Bengali data in signup/login forms
14 | Test if user can update his profile/card number after login
15 | Test searching functionality using exact match & fuzzy search
16 | Test if only logged in users can add a product into cart/wishlist
17 | Test if logged in users can remove a product from cart/wishlist
18 | Test if product amount in cart matches the amount of all products chosen by user
19 | Test if user can proceed to payment using card
20 | Test if user successfully makes a purchase
21 | Test if user gets confirmation upon successful purchase
22 | Test if user Is able to make multiple purchase with the same card several times back to back
23 | Test if user is getting email notifications after each successful purchase
24 | Test if user finds the status of each purchase request properly
25 | Test if product details are shown completely in each product page
26 | Test for some loading animation in UI after making a service call to backend
27 | Test searching functionality according to different categories & sub-categories
28 | Test if loggedin users can logout successfully
29 | Test if popular card options are accpeted, e.g. mastercard, VISA etc
30 | Test server functionality at peak hours e.g. when some discounts are given
31 | Test the URL paths if they correspond to appropriate pages

## Sample Test report
Sample Test report
Sprint | 1
Total Testcases | 30
Coverage | 98%
Total Passed | 27(90%)
Total Failed | 3(10%)

## Sample bug report
Sample bug report
ID | Title | Description | Category/level | Priority | Severity | Status | Tracker ID
1 | Product image is not showing | When user goes into a product page, product image is not showing | Enhancement | high | high | Open | B-5
2 | Product can not be removed from cart | After adding a product to cart, user can not find the option to remove it from cart | Enhancement | high | high | open | B-7
3 | Bengali translation is missing for Alert messages in sign up page | Signup page is showing alert messages in English when Language mode is selected Bengali | Enhancement | high | low | open | B-8
4 | Login page alignment is broken in android app | In android app(version 7), login page component looks clipped on the right | UI/UX | low | medium | fixed | B-10
5 | Credit Card number is being stored in browser cache memory | After user makes 1st purchase using card, h/she can see the card number while making the 2nd purchase which is coming from browser's cache. | Security | high | low | open | B-11